## Sheet1
Request# | Description | Date of request | Priority | Requested by | Implemented by | Status | Status Date | Ver | Comments
1 | implement global stats | 2014-11-01 | medium | Wing | LiliaMesina | Done | 2014-11-11 | v2.0
2 | make tresholds available in batch mode | 2014-11-30 | high | Sutherland | LiliaMesina | Done | 2014-12-01 | v2.1
3 | get analysis for red channel also | 2014-11-25 | high | Sutherland | LiliaMesina | In progress | 2014-12-01 | v2.2 | on GitHub
As of v2.2 | Issues list moved to GitHub Project Repository